## Sheet1 (hidden)
Module | Task Name | Comments
Carrier Settings | UI Design | Released to QA. Support for QA bugs in progress. No open QA issues from UI side as of now.
Service Integrations and Issue Fixes
UI changes as per mock up since earlier we have referred Dev URL
QA Bug Fixes
Common Component Integration like headers, Tabs and SubTabs, BreadCrumbs
Service Contract Modifications and UI Changes for that
Writing Company | UI Design | Done with UI changes, Due to some requirement changes on Rate-Plans tab, its on-hold
Service Integrations and Issue fixes
Service Contract Modifications and UI Changes for that
Entity Management | UI Design | Released to QA for Obligees, Consultant and Financial Institutions
Service Integrations and Issue fixes
Service Contract Modifications and UI Changes for that
Common Components Integrations like below, Header Component , Tabs and Sub Tabs, BreadCrumbs. Grid Action Column. Content handler.
Accounts | UI Design | Development In Progress
Common Component Integration like headers, Tabs and SubTabs, BreadCrumbs, Ck-Editor
Common UI Development | Chips Component Development | Common components and common validators are created by us to re-use across all the modules
Phone Masking and Validators for Email, Phone, Website and Postal Code
Directives for Allow Numbers, Allow only Alpha Numeric
CK-Editor Component
Shared Module for Business - In Progress

## Team (hidden)
Module Name | Resource Count | Resource Name
UI - Carrier Settings - QA - Support | 1.5 | Yokini Subbu
UI - Entity Management - QA - Support
UI - Accounts | 2.5 | Suresh Mani Barakath (0.5)
Forms Designer | 1 | Sithi
Planning and Discussion | 0.5 | Subbu
Module Name | Resource Count | Resource Name
UI - Accounts | 2.5 | Suresh
Mani
Barakath (0.5)
Forms Designer | 1 | Sithi
Planning and Discussion | 0.5 | Subbu
General UI Revision | 1.5 | Yokini
UI - Carrier Settings - QA - Support |  | Subbu (0.5)
UI - Entity Management - QA - Support

## Tasks Allocation
Module | Task | Resource | ETA | Comments
Accounts | § Business
| o Assessment – Updated Requirement Changes | Barakath | 2019-09-03
§ Individual
| o Third Parties | Manikandan | 2019-09-03
| o Grid List | Manikandan | 2019-09-03
| § Account | Suresh
| o Parties | Suresh | 2019-09-03
| o Browse | Suresh | 2019-09-04
| o Creation | Suresh | 2019-09-03
| o Key Contacts | Manikandan/Subbu | 2019-09-03
§ Bonds
| o Contract | Manikandan | 2019-09-04
| o Commercial | Manikandan | 2019-09-04
| o Bond Submission | Suresh | 2019-09-05
| o Bonds | Suresh | 2019-09-05
§ Shared Components
| o Text Editor Changes for additional Tool bars (Print) | Suresh | 2019-09-05
| § Overview - Text Editor for additional Tool bars Integration |  | 2019-09-05
§ Financials
| Base Structure and Sub Tabs / BreadCrumbs | Suresh | 2019-09-06
| Carrier - QA Bugs | Subbu | 2019-09-06
| Entity Management QA Bugs | Subbu/TBD | 2019-09-06
Accusoft | Side Bar - Merge Fields | Yokini
Postion Tab
| Units | P0 | Points is fine.
| Position | P0 | Coordinate Position
| Left | P0 | Coordinate Position
| Right | P0 | Coordinate Position
| Width | P0 | Width dimension of the field
| Bottom | P0 | Coordinate Position
| Top | P0 | Coordinate Position
| Height | P0 | Height dimension of the field
| Image | P0
| Radio Button | P0
| ToolTip | P0
| Print | P0
| Right Click Options | P0

## Sheet2
City Drop Down Changes
State DDL Change
City - Text Box
Hours Per 1 City DDl Change and Testing
Carrier Settings | 3 | 1 | 4
Writing Company | 1 | 1 | 1
Entity Management |  | 1 | 1
Accounts |  | 0.3 | 1
Entity Management | Obligee Location
Carrier Settings | re work
Writing Company
Entity Management

## Tasks
Task Name | Screen | Efforts in hrs | Assigned To
City DDL changes in UI | Carrier Settings | 4
| Writing Company | 1
| Entity Management | 1
| Accounts | 1
Accounts - Service Integration | Manage Accounts | 4 | Suresh
| Account Parties | 4 | Suresh
Business - Third Party | Consultant - Add (on Fly) | 16 | Suresh | Need to create as shared component with service integration
Accounts - Updated Requirements | Overview - Action Items | 12 | Mani | Need to review updated requirements pro actively and need to do changes accordingly
Breadcrumbs | Narrative, Comments, Key Docs |  |  | Bread Crumbs - Overview should be link
Status Popup | Entity Mangement | 8 | Yokini
Primary Contact and Location Cards | Entity Mangement | 4 | Yokini
| Account Business / Individual | 4 | Yokini
Account | Overview - Summary UI changes | 8 | Mani
| Action Button style changes | 2 | Suresh

## Account -Services
Main Tabs | Service | Operation | Status | Comments
Manage Accounts | AccountAccess | Persist | Dev-Completed | Database schema and Integration Test Cases are pending.
|  | Get | Dev-Completed
|  | GetList | Dev-Completed
| AccountManager | CreateAccount | Dev-Completed
|  | Get | Dev-Completed
|  | GetAccountList | Dev-Completed
Account Parties | AccountAccess | GetAccountEntityList | Dev-Completed
|  | PersistAccountEntity | Dev-Completed
| AccountPartiesManager | Persist | Dev-Completed
|  | GetList | Dev-Completed
Account Overview | AccountOverviewManager | PersistAccountComment | Dev-Completed
|  | GetAccountCommentHistory | Dev-Completed
|  | GetAccountCommentList | Dev-Completed
Main Tabs | Service | Operation | Status | Comments
Account Parties | BusinessManager | GetInitialState | Dev-Completed | As discussed, Agency related changes are pending.
|  | Persist | Dev-Completed | Integration Test Cases are pending.
|  | Delete | Dev-Completed
| BusinessLocationManager | GetList | Dev-Completed
|  | GetLocation | Dev-Completed
|  | Persist | Dev-Completed
|  | Delete | Dev-Completed
| BusinessContactManager | GetList | Dev-Completed
|  | Persist | Dev-Completed
Main Tabs | Service | Operation | Status | Comments
Account Parties | IndividualManager | GetInitialState | Dev-Completed | As discussed, Agency and Location related changes are pending,Integration Test Cases are pending..
|  | GetIndividual | Dev-Completed
|  | GetIndividualList | Dev-Completed
|  | DeleteIndividual | Dev-Completed
|  | PersistIndividual | Dev-Completed
| ExperienceCapabilitiesManager | GetWorkTypeList | Dev-Completed
|  | GetNatureOfWorkList | Dev-Completed
|  | GetSICCodesList | Dev-Completed
|  | GetNAICSCodesList | Dev-Completed
|  | GetLicenseTypeList | Dev-Completed
|  | GetExperienceAndCapabilities | Dev-Completed | As discussed, Persisting all the experience and capabilities data at a single save
|  | PersistExperienceAndCapabilities | Dev-Completed
|  | GetCertifications | In Progress
Tab/Section | Service Name | Resource Name | Is Service Ope Imp Completed? | Is Int Testing completed? | Is Ready for UI Integration? | Comments | UI Resource
Accounts -> Create, Search, Get | AccountContracts | Mahesh | Yes | Yes | Yes | Other UI screen dev Inprogress
| AccountAccess | Mahesh | Yes | Yes | Yes | Other UI screen dev Inprogress
| AccountManager | Mahesh | Yes | Yes | Yes | Other UI screen dev Inprogress
Parties -> Search, Add, Edit and Delete | AccountPartiesManager | Mahesh | Yes | Yes | Yes | Other UI screen dev Inprogress
Account -> Overview | AccountOverviewManager | Mahesh | Yes | Yes | Yes | Other UI screen dev Inprogress
Account -> Default Information | AccountDefaultInformationManager | Mahesh | No | No | No | Dev Inprogress
Account -> Bond | AccountBondManager | Mahesh | No | No | No | Yet to start
Account -> Parties -> Add Bus, Bus Profile | BusinessManager | Vaishali | Yes | Yes | Yes
| BusinessLocationManager | Vaishali | Yes | Yes | Yes
| BusinessContactManager | Vaishali | Yes | Yes | Yes
Account -> Parties -> Add Ind, Ind Profile | IndividualManager | Praneeth | Yes | Yes
| IndividualLocationManager | Praneeth | No | No
Account -> Parties -> Exp & Capabilities | ExperienceCapabilitiesAccess | Praneeth | Yes | Yes
| ExperienceCapabilitiesManager | Praneeth | Yes | Yes
Account -> Parties -> Third Parties | AccountantContracts | Vaishali | Yes | Yes | Yes
| AccountantManager​ | Vaishali | Yes | No | No | In Progress
| AccountantLocationManager | Narender | Yes | Yes
| AccountantContactManager | Narender | Yes | Yes
| FinancialInstitutionContracts | Narender | Yes | Yes
| FinancialInstitutionManager | Narender | Yes | No
| FinancialInstitutionLocationManager | Narender | Yes | Yes
| FinancialInstitutionContactManager | Narender | Yes | Yes
| FinancialInstitutionAccountManager | Mahesh | No | No | No | Yet to start
| InsuranceContracts | Praneeth | Yes | Yes
| InsuranceManager | Praneeth | Yes | Yes
| InsuranceLocationManager | Praneeth | Yes | Yes
| InsuranceContactManager | Praneeth | Yes | Yes
| InsurancePolicyAccess | Mahesh | Yes | Yes | Yes
| InsurancePolicyManager | Mahesh | Yes | Yes | Yes
| TradeReferencesContracts | Praneeth | Yes | Yes
| TradeReferencesManager | Praneeth | Yes | Yes
| TradeReferencesLocationManager | Praneeth | Yes | No
| TradeReferencesContactManager | Praneeth | Yes | No
| ConsultantContracts | Mahesh | Yes | Yes | Yes | Existing service and no changes as part accounts.
| ConsultantAccess | Mahesh | Yes | Yes | Yes | Existing service and no changes as part accounts.
| ConsultantManager | Mahesh | Yes | Yes | Yes | Existing service and no changes as part accounts.
| ConsultantLocationManager | Mahesh | Yes | Yes | Yes | Existing service and no changes as part accounts.
| ConsultantContactManager | Mahesh | Yes | Yes | Yes | Existing service and no changes as part accounts.

## Ramp-Up
Sl. No | Task description | Estimated Hours
1 | Business Domain Overview, Application Walkthrough Sessions | 2
2 | Code Walkthrough Sessions | 2
3 | Developer Workstation Setup | 2
4 | Understand Coding Standards (UI / Services appropriately) | 2
5 | Understand UI Screen Standards https://zeroheight.com/0a1a82a6b/p/961e2f | 2
6 | Assign low priority bugs and development tasks and have them work on it. | Actuals
7 | Review the work performed by team members | Actuals
8 | Development of a sample screen and implement CRUD Operations and some of the tasks below | 40
NON BILLABLE
Create Angular App
Implement Left Nav and Menu https://zeroheight.com/0a1a82a6b/p/961e2f
Create Header https://zeroheight.com/0a1a82a6b/p/961e2f
Implement Login and Log out
Implement Authentication and Authorization
Implement Services Integration. Use Fake Json for Service calls https://jsonplaceholder.typicode.com/
Learn debugging and troubleshooting